## Introduction
Project Name
What is this? | This workbook is meant to help manage and piroritize the user stories and features using scrum.
How to use and read this document? | Before project start: The product owner is responsible for managing and maintaining the product backlog of user stories.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells that you can edit have a blue background.
Sprints are assumed to be 2 weeks long (10 working days)/
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.

## Product backlog
Book Management System
| Organizations | Backend Development Team Backend & Database Team Backend & Frontend Team Frontend & Backend Team Database Team Security Team Frontend Development Team QA & Testing Team
| Project | Bookstore Management System
| Product Owner | John Kinney
| Scrum Master | Lary Hezekiah
| Development Team | Latherio Kidd
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility
S1-001 | User Authentication & Role-Based Access | As a bookstore staff member, I want to log in securely so that I can access system features based on my role. | Successful login with valid credentials; Unauthorized users restricted; Multi-factor authentication enabled. | High | Sprint 1 | Backend Development Team
S1-002 | Inventory Management - Book Tracking | As a store manager, I want to track books from entry to sale so that inventory is always accurate. | Books can be added, edited, removed; Inventory updates in real-time; Low-stock alerts generated. | High | Sprint 1 | Backend & Database Team
S1-003 | Sales Processing - Point of Sale (POS) | As a cashier, I want to process transactions so that customers can complete their purchases quickly. | Sales recorded with timestamps; Payment integration works; Receipts generated. | High | Sprint 1 | Backend & Frontend Team
S1-004 | Customer Order Management - Cart & Checkout | As a customer, I want to add books to a cart and check out so that I can complete my purchase online. | Users can add/remove items from cart; Orders are confirmed via email; Payment is processed securely. | Medium | Sprint 1 | Frontend & Backend Team
S1-005 | Database Setup & Optimization | As a developer, I want a well-structured relational database so that all system data is stored efficiently. | Database schema designed; Relationships between tables defined; Optimized for fast queries. | High | Sprint 1 | Database Team
S1-006 | Security & Compliance Measures | As a security analyst, I want the system to be secure so that customer and business data is protected. | Passwords encrypted; PCI-compliant payment processing; Audit logs implemented. | High | Sprint 1 | Security Team
S1-007 | User Interface (UI) Design - Admin & Customer Dashboards | As a UI designer, I want a responsive interface so that users can navigate the system easily. | Admin panel designed; Customer dashboard functional; Mobile responsiveness ensured. | Medium | Sprint 1 | Frontend Development Team
S1-008 | Testing & Quality Assurance | As a QA engineer, I want to conduct rigorous testing so that system functionalities work as expected. | Unit tests cover 90%+ of code; Integration tests for key features; User acceptance testing completed. | High | Sprint 1 | QA & Testing Team
S1-009 | User Authentication - Multi-Factor Authentication | As a security analyst, I want multi-factor authentication (MFA) enabled so that unauthorized access is prevented. | Users must verify via OTP or authenticator app; MFA required for admin logins; Option to enable/disable MFA in settings. | High | Sprint 1 | Security Team
S1-010 | Inventory Management - Barcode Scanning | As a store manager, I want barcode scanning enabled so that book inventory updates are faster and more accurate. | Barcode scanner integrates with inventory system; ISBN lookup auto-fills book details; Supports manual entry fallback. | High | Sprint 1 | Backend & Frontend Team
S1-011 | Sales System - Discount & Promotions | As a cashier, I want a discount system so that I can apply promotions to customer purchases. | Cashiers can apply discounts during checkout; System auto-applies valid promotions; Discounted total displayed before payment. | Medium | Sprint 1 | Backend & Frontend Team

## Sprint 1
|  | Project |  | Book Management
|  | Sprint # |  | 1
|  | Start date |  | 2025-02-25
|  |  | Total Team Members | 3
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00
1 | NF-001 | Sprint Planning Meeting | Scrum Master (Lary Hezekiah) facilitates, Latherio Kidd, Cody Peterson, John Kavanaugh | 2
2 | NF-002 | Infrastructure Setup (Backend, Database) | Backend & DevOps (Latherio Kidd) | 8
3 | NF-003 | Daily Standup Meetings | Scrum Master (Lary Hezekiah), All Members | 5
4 | NF-004 | Code Review & Internal Testing | Latherio Kidd, Johnathan Kavanaugh | 6
5 | NF-005 | Sprint Review | Scrum Master, All Members | 2
6 | NF-006 | Sprint Retrospective | Scrum Master, All Members | 2
7 | S1-001 | Develop user authentication & role based access control | Backend (Latherio Kidd) | 16
8 | S1-002 | Implement inventory management system for book tracking | Backend & database ( Latherio Kidd | 20
9 | S1-003 | Design wireframes for Login, Inventory, Book edits views | Front-End (Johnathan Kavanuagh) | 6
10 | S1-004 | Develop HTML/ CSS Layout for core Views | Front- End( Johnathan kavanuagh) | 8
11 | S1-005 | Draft User Stories and acceptance critieria ( e.g. Inventory CRUD) | Product Owner ( Cody Peterson) | 4
12 | S1-006 | Define system variable conventions and naming standards |  | 3
13 | S1-002 |  |  | 20
Remaining units (actual)
Remaining units (ideal)
[10 empty] | 0 | [6 empty] | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0

## Sprint 2
|  | Project |  | Bookstore Management System
|  | Sprint # |  | 2
|  | Start date |  | 2025-03-04
|  |  | Total Team Members | 3
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00
9 | S2-001 | Develop sales processing & POS integration | Backend & Frontend (Latherio Kidd, John Kavanaugh) | 10
10 | S2-002 | Implement customer order management (Cart & Checkout) | Frontend & Backend (John Kavanaugh, | 10
11 | S2-003 | Set up and optimize the database | Database (Latherio Kidd) | 6
12 | S2-004 | Implement security & compliance measures | Security & Compliance (Latherio Kidd, John Kavanaugh) | 5
13 | S2-005 | Design and develop UI for admin & customer dashboards | Frontend (John Kavanaugh) | 8
14 | S2-006 | Conduct testing & quality assurance | QA ( Scrum Master) & Testing (Latherio Kidd, John Kavanaugh, Cody Peterson) | 6
15 | S2-007 | Enable multi-factor authentication (MFA) | Security (Latherio Kidd), Product Owner (Cody Peterson) | 4
16 | S2-008 | Integrate barcode scanning for inventory management | Backend & Database (Latherio Kidd) | 6
17 | S2-009 | Refine Backlog and acceptance crititeria for new features | Product Owner ( Cody Peterson) | 3
18 | S2-010 | Review UI/ UX for usability and consistency | Product Owner ( Cody Peterson) | 3
Remaining units (actual)
Remaining units (ideal)
[10 empty] | 0 | [6 empty] | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0